## Energy & Store Upgrades
Priority | FSC Energy Efficiency, Store & Building Needs | Lead | Cost | Savings/Year | Info | Heat Pumps: Total Labor | 5700
PHASE 1 | COMPLETE or IN PROGRESS |  |  |  |  | Total Materials | 25200
DONE | Heat Pumps | Zizi, Emmy | 24000 | 4000 | Tim Adams, EcoHeat Maine, installed September/October 2015 (See final costs.) Program efficiency settings and train staff and tenants on controls. | Subtotal | 30900 | REBATES
by 11/15 | LED Lighting | Zizi, Emmy | 1700 | 1700 | Efficiency Maine program through Flanders Electric, Heath Poland ($6,800 total) Efficiency Maine: $6800 total, we pay $1700 with that money back in savings within one year. Signed paperwork 10-13-2015, install within 3-4 weeks. | Tax | 1386 | Efficiency Maine $7500
DONE | Kitchen Stove Pilots | Wendy | 0 | 1463 | Sold stove for $500. Propane cost for stove was $1250. Replacing with donated stove from Wendy's sister, need 220 outlet wired. | Total | 32286 | Fujitsu $3000
NEW COOLER & 220V
| New Produce Cooler |  | 13374
| 220V Outlet wired for stove in kitchen |  | 200 |  | Need quote ($200–$1000)
39274
PHASE 2 | PRIMARY ENERGY AUDIT COSERVATION MEASURES
1 | West Wall Insulation and Siding |  | 1500 | ? | NEED ESTIMATE: Scott's quick estimate… Labor 30 hrs @ 40/hrs, cleanup to dump, materials: repack and add insulation, add exterior plywood, caulk and paint. 1 inch polyiso over clapboards, aluminum siding.
2 | Insulate Foundation | Tinsleys | 1000 | 1800 | $2,000 Cellar insulation (1- to rim joists and above grad, 1k- 2 feet worth) Northeast Insulation, Paul 887-9168
3 | Relocate compressors (move to SE inside corner -or- outside) | Mary Ann, Don Maclean | 8500 | ? | NEED ESTIMATE Cobb - $8000 - THAYER The total cost to do this work is: $8,500.00 The cost for only refrigeration work is: $4,800.00 Labor 2,800.00 Materials 2,000.00
4 | Build wind tunnel for compressors |  | 500 | ? | NEED ESTIMATE Materials and labor | For a typical home* in Portland, Me choose ENERGY STAR certified windows and save: $358 a year when replacing single pane windows. $84 a year over non ENERGY STAR qualified double-paned, clear glass replacement windows. Assumptions: Savings estimates based on an even mix of 1,700 sq. ft one-story and 2,600 sq. ft two-story homes with natural gas heat and electric air conditioning.
5 | Window Insulation/Coverings and/or install large fixed panes front of building | Jess Lilly, Zizi | 1112.98 | 324 | Front Store Windows only: EnergySavr saved in shopping cart http://www.windowinserts.com/home.php Info under zizi's account.) #1 Sorefront Side Windows: There are two of these windows 21 sqft x 2 = 42 sqft Pane size is – 35 inches wide and 73 inches tall ($94.79 x 2 = $189.58) Frame size – 42 inches wide and 98 inches tall (This is including the small pane at the top) #2 Sorefront Front Windows: There are two of these windows 15 sqft x 2 = 30 sqft Pane size is – 112 inches wide and 73 inches tall ($195.34x2=$390.68) Frame size is – 119 inches wide and 80 inches tall #3 Boothby Office: 4.5 sqft x 8 = 36 sqft Including the frame: 58 inches wide and 45 inches to the bottom of the stained glass Inside of the frame: 50 ½ inches wide and 45 inches to the bottom of the stained glass **Two windows which are already replacement windows which do not need to be replaced at this point, major concern would be the stained glass in the offices upstairs. Stained glass: 50 ½ inches wide and 16 inches tall (there are three of these windows) #3 Norway Downtown Office: Stained glass: 50 ½ inches wide and 16 inches tall (there are three of these windows) #3 SE Office: Stained glass: 50 ½ inches wide and 16 inches tall (there are two of these windows) ($56.44x8=$435.528) TOTAL 912.99+199.99 Shipping = $1,112.98 108 sqft x $6.00 = $324
6 | Loading door flaps |  | 200 | ? | Will help the heat pumps from working harder to regain temps when air temps drop suddenly
7 | Insulate Water Heater, Pipes, 7-day timer | Tinsleys | 113 | 45 | Jackets for old water heaters - $23 plus the pipe insulation. Lowell Lumber in Buckfield. Need to know how much pipe to insulate. $60 for case (210 linear feet). $50 water heater timer.. http://energy.gov/energysaver/projects/savings-project-insulate-your-water-heater-tank
|  | TOTALS | 12925.98 | 2169
OPTIONAL
8 | Walk-In Cooler Economizer |  | 4576 | 782 | NEED NEW ESTIMATE do we know what each of the major equipment pieces uses for electricity? The walk-in, freezer, beer cooler? Can we find out without an act of Congress? So we could see whether $$ for economizer in like the walk-in cooler is a reasonable return on our investment? Economizer on medium temperature (>32° F) walk-in coolers. Economizers use cold winter air to help cool product.
9 | Replace Soffit Plugs |  | 400 | - | NEED ESTIMATE What's wrong with the plugs now? Estimate of 100 plugs at $2 each = $200, plus labor.
10 | Insulate Ceiling with Foam | Tinsleys | 9000 | 100 | $9,000 The roof would be R40, 6 inch ( 40 x 40 feet) (Get opinion of engineer to understand if we should do this now with the heat pumps installed. Concern raised about "balloon effect" of heat needed in building design to melt snow on flat roof. —ZV) http://www.cellulose.org/HomeOwners/CalculateSavings.php
11 | Motion Detector Lighting | Zizi | 180 | - | RECONSIDER: Ask Flanders if this will help now that we have LEDs? $15/each, need 12: 2x basement, 3x bathrooms, 2x 2nd floor steps (front, back), 1x 2nd floor hallway, 1x 2nd floor sunpace, 1x kitchen, 1x stockroom, 1x garbage room
Check it off | Turn hot water off or Install on-demand water heater for 2nd floor |  | 0 | 0 | The idea on the water heater is that we waste a lot having it go up to the 2nd floor just to that one sink, I think. Better to cut that off and not have it drain the system, then to keep it going. I think that Claire thought it would be better to just have cold water going to that one sink.
No | Foundation Inusulation Paint |  | 1000 | 0 | Builders Installed - (Suggestion to paint the foam insulation for fire, another 1k) Tom 339-9797 (Recommend that we do not do this. Flame retardents unecessary and toxic. —ZV)
No | Kitchen Vent controlled with thermostat |  | 0 | 0 | This seems like a non-issue for now.
|  | TOTALS | 15156 | 882
PHASE 3 | MAINTENANCE & LONGTERM GOALS
1 | Paint exterior and doors |  | 10000 |  | FSC reimbursed Zizi for driveway lower wall paint, 1.5 gallons left.
2 | Solar PV System |  | 100000 |  | Explore incentives from State

## Finances
Resources available |  |  |  | for what projects
Rural Development Loan |  |  |  |  | 34000
Rural Development grant |  |  |  |  | 17500
Efficiency Maine rebates |  |  |  |  | 5200
Jason Shiers contribution |  |  |  |  | 500 |  | toward the $1500 needed for construction account
sale of copper and basement contents | [5 empty] | ?? | board fundraiser | $2.00/# and upwards?
Indiegogo campaign |  |  |  |  | 20000
sell american gas range |  |  |  |  | 500
77700
Project Cost Item | User Desc | Item Cost
Legal Services | To Close Loan |  | 1266 |  |  |  | actual from Dana was $850 I think.
Develop. | Install prod. cooler |  | 1500
Other | Freight Charge |  | 675 | 13374
Equipt | Coolers (tax incl) |  | 11199
Develop. | Labor and Taxes |  | 6360
Equipt | Heat Pump Materials |  | 32000
staff hours |  | 2% @ $11/13 per hour
devoted to work projects above reg hour
cost overruns |  | 5%
reserve account |  | 24.40 per month till 2928. |  |  |  |  | to be included in 2016 budget and out of what portion of this years budget?
legal services |  |  | included up to 1266.